## Sheet1
WBS | Task Name | Duration | Resource
1 | Requirement Analysis
1.1 | Develop Project Charter
1.1.1 | Identify Goals and Objectives | 1d | Srikanth
1.1.2 | Identify High Level Budget | 2d | Srikanth
1.1.3 | Develop, Review, Approval - Project Charter | 4d | Srikanth
1.1.4 | Stakeholder Meeting - Internal Team | 0.5d | CEO, Srikanth, Marketing Manager, IT Manager
1.2 | Develop Preliminary Project Scope Statement
1.2.1 | Functional Requirements | 3d | Marketing Manager
1.2.2 | Non Functional Requirements | 3d | IT Manager
1.2.3 | High Level Time Schedule | 1d | Srikanth
2 | RFP and Vendor Selection
2.1 | Create Request for Proposal | 5d | Srikanth
2.2 | Shortlist Vendors for Circulation | 3d | Srikanth
2.3 | RFP Consolidation and Analysis | 2d | Srikanth
2.4 | Finalize Vendor | 1d | Srikanth
2.5 | Project Kickoff Meeting | 0.5d | Vendor, Internal Team
2.6 | Design Phase Complete | 0d
3 | Implementation
3.0.1 | Weekly Status Meeting | 0.5d | Vendor, Internal Team
3.1 | Functional Specifications Document (FSD)
3.1.1 | 1st Review | 2d | Srikanth
3.1.2 | 2nd Review | 2d | Srikanth
3.1.3 | Approval | 1d | Srikanth
3.2 | Technical Specifications Document (TSD)
3.2.1 | 1st Review | 2d | IT Manager
3.2.2 | 2nd Review | 2d | IT Manager
3.2.3 | Approval | 1d | IT Manager
3.3 | Test Plan Strategy
3.3.1 | Setup Internal Testing Team | 1d | IT Manager
3.3.2 | Review and Approve Test Plan | 3d | IT Manager
3.4 | UAT (User Acceptance Testing) Document
3.4.1 | Review UAT Document | 2d | IT Manager
3.4.2 | Approve UAT Document | 1d | IT Manager
3.5 | Mock Demo - First
3.5.1 | First Demo Meeting | 1d | Vendor, Internal Team
3.5.2 | Review Notes for First Mock Demo | 1d | Marketing
3.6 | Content Handover
3.6.1 | Consolidation of Media Content for Website | 2d | Marketing
3.6.2 | Peer Review and Internal Approval | 1d | Marketing
3.6.3 | Hands-on Content Upload + Observations | 2d | Marketing
3.7 | UI Branding Elements Handover
3.7.1 | Branding Requirements Doc | 1d | Marketing
3.7.2 | Branding Media Assets Handover | 1d | Marketing
3.8 | Mock Demo - Second
3.8.1 | Second Demo Meeting | 1d | Vendor, Internal Team
3.8.2 | Review Notes for Second Mock Demo | 1d | Marketing
4 | Acceptance Testing
4.1 | Setup Internal Team for UAT | 1d | IT Manager
4.2 | UAT (User Acceptance Testing) | 3d | IT Manager
4.3 | Implementation Phase Complete | 0d
5 | Deployment
5.1 | Deployment Guide
5.1.1 | Review and Approve UAT Document | 2d | IT Manager
5.1.2 | Hardware and Software Infra | 5d | IT Manager
5.2 | Deploy Infra
5.2.1 | Deployment Architecture setup | 3d | IT Manager
5.2.2 | Preliminary Tech Stack Installation | 3d | IT Manager
5.2.3 | Staging and Production Server Testing | 2d | IT Manager
5.3 | Deployment Complete | 0d
6 | Training and Handover
6.1 | Training Strategy
6.1.1 | Schedule Training for Users | 2d | HR Manager
6.1.2 | Learn-by-doing Sessions | 5d | HR Manager
6.2 | User Manual
6.2.1 | Review and Approve User Manual | 2d | Marketing Manager
6.2.2 | Controlled Distribution to Stakeholders | 1d | Marketing Manager
6.3 | Handover | 0d

## Sheet2
WBS | Task Name | Duration
0 | Plan for Corporate Website Development
1 | Requirement Analysis
1.1 | Develop Project Charter
1.2 | Develop Preliminary Project Scope Statement
2 | RFP and Vendor Selection
2.1 | Create Request for Proposal
2.2 | Shortlist Vendors for Circulation
2.3 | RFP Analysis
2.4 | Finalize Vendor
3 | Implementation
3.1 | Requirements Specification Document
3.2 | Technical Specifications Document
3.3 | Test Plan Strategy
3.4 | UAT (User Acceptance Testing) Document
3.5 | Mock - First
3.6 | Content Handover
3.7 | UI Branding Elements Handover
3.8 | Mock - Second
4 | Acceptance Testing
4.1 | Setup Internal Team for UAT
4.2 | UAT (User Acceptance Testing)
5 | Deployment
5.1 | Deployment Guide
5.2 | Deploy Infra
6 | Training and Handover
6.1 | Training Strategy
6.2 | User Manual
6.3 | Handover

## Sheet3
WBS | Task Name | Duration
0 | Plan for Corporate Website Development
1 | Requirement Analysis
2 | RFP and Vendor Selection
3 | Implementation
4 | Acceptance Testing
5 | Deployment
6 | Training and Handover
`