## WBS - Tasks - Office Move Plan
Get Approval from Board, Departments | 2d | FS
Initiate Project | 1d
Resource Plan for Approval | 2d | SS
IT Infra Plan for Approval | 2d
Seating Arrangement Floor Plan | 2d | FF
Electrical Layout Plan | 2d
Initiate final bills due - Existing Infra | 1d | SF
Open new accounts New Infra | 1d
Space selection & Site Surveys | 5d
High Level BUDGET Approval | 5d
Hire Interior Designer (ID) Consultant | 5d
Furniture Criteria and Specifications | 5d
Create Furniture Inventory | 2d
Decision - Reuse/Repurpose/Purchase/Sell Furniture | 5d
High Security areas - identify needs | 2d
Fire regulations and planning | 2d
Monitoring requirements | 2d
Security Vendor Requirements | 2d
Security Plan Approval | 2d
Inventory of all IT assets | 3d
IT Server hosting requirements | 2d
Network layout plan | 5d
Vendor selection for IT Networking | 5d
Telephone System - New or Reuse - Action Plan | 2d
Order New or Relocation of Telephone System | 2d
INTERNAL Communications Plan | 5d
EXTERNAL Communications Plan | 5d
Document Management Plan | 3d
Offsite Storage Needs | 3d
Onsite Storage Needs | 3d
Filing Requirements of Departments | 2d
Old Documents Disposal (Incl. Sensitive) | 2d
Select Move Coordinators by Department | 4d
VENDOR Finalize - Movers and Packers | 1d
Schedule Building Restrictions | 1d
Schedule Elevator Access - Origin & Destination | 1d
Finalize Movement Dates | 2d
Finalize Sequence of Movement | 0.5d
Furniture Shifting | 0.5d
Servers Shifting and Setup | 3d
Networking and Commn Setup | 3d
Inspections and Testing Final | 1d
Computers/Workstations Shifting | 1d
Documents Shifting | 1d
Security Inspection | 1d
Office Shifting COMPLETE | 1d

## WBS with SUMMARY TASKS
Notes
PROJECT DEVELOPMENT
Get Approval from Board, Departments | 2d
Initiate Project | 1d | FS
Resource Plan for Approval | 2d
IT Infra Plan for Approval | 2d | SS
Seating Arrangement Floor Plan | 2d
Electrical Layout Plan | 2d | FF
Initiate final bills due - Existing Infra | 1d
Open new accounts New Infra | 1d | SF
PROJECT PLANNING
Space selection & Site Surveys | 5d
High Level BUDGET Approval | 5d
Hire Interior Designer (ID) Consultant | 5d
INTERIOR DESIGN AND LAYOUT
Furniture Criteria and Specifications | 5d
Create Furniture Inventory | 2d
Decision - Reuse/Repurpose/Purchase/Sell Furniture | 5d
SECURITY REQUIREMENTS
High Security areas - identify needs | 2d
Fire regulations and planning | 2d
Monitoring requirements | 2d
Security Vendor Requirements | 2d
Security Plan Approval | 2d
IT AND NETWORKING
Inventory of all IT assets | 3d
IT Server hosting requirements | 2d
Network layout plan | 5d
Vendor selection for IT Networking | 5d
Telephone System - New or Reuse - Action Plan | 2d
Order New or Relocation of Telephone System | 2d
COMMUNICATIONS REQUIREMENTS
INTERNAL Communications Plan | 5d
EXTERNAL Communications Plan | 5d
DOCUMENT MANAGEMENT
Document Management Plan | 3d
Offsite Storage Needs | 3d
Onsite Storage Needs | 3d
Filing Requirements of Departments | 2d
Old Documents Disposal (Incl. Sensitive) | 2d
MOVE FINAL PREPARATIONS
Select Move Coordinators by Department | 4d
VENDOR Finalize - Movers and Packers | 1d
Schedule Building Restrictions | 1d
Schedule Elevator Access - Origin & Destination | 1d
Finalize Movement Dates | 2d
OFFICE - PHYSICAL SHIFTING
Finalize Sequence of Movement | 0.5d
Furniture Shifting | 0.5d
Servers Shifting and Setup | 3d
Networking and Commn Setup | 3d
Inspections and Testing Final | 1d
Computers/Workstations Shifting | 1d
Documents Shifting | 1d
Security Inspection | 1d
Office Shifting COMPLETE | 1d | Make this a Milestone