## AIMS Checklist
Check List for AIMS for project
SN | Particulars | Scope | Status-User | Status-SSM
A | Hardware Requirements - Make arrangement from Store to Plant/Factory
1 | Server CPU & Monitor for X-Force AIMS | User
2 | Power supply arrangement for all supplied hardware by SSM InfoTech. | User
3 | Cabling part related to alarms communication | User
4 | Hardware firewall configuration- As per architecture | User
5 | (User System – AIMS – End User Intranet) | User
6 | OPC AE alarms communication through hardware firewall, necessary software to be provided by User. I.e. MatrikonOPC Tunneller tool and its configuration at AIMS end. | User
7 | OPC AE Client- Application installation rights- In DCS Station- If required | User
8 | Voice call- Analogue telephone line – If required on site as per specs. | User
9 | SMS Functionality- 3G GSM SIM card to be provided by User with appropriate network strength. | User
10 | Reports customization – Predefine formats, data or identification to be provided | User
11 | Alarms & events identification to be provided by User to configure color coding and Alarm type in X-Force AIMS system. | User
12 | I.e. Alarms, events, return, Operator action, system alarm, messages, process or Non process alarms identification. To attend clause no. 5.13.5.5 | User
13 | Operator guidance message – probable reasons listing to be provided by DCS vendor | User
14 | Level wise priority distribution, color code, string should have unique identification for detail configuration | User
15 | Alarms segregation identification for customization at any stage as per specification | User
17 | Serial expansion card - Serial Port connectivity | SSM
18 | GSM Modem box | SSM
19 | Voice modem box - Hiro Voice Modem | SSM
20 | ADAM 4068 DO Module box | SSM
22 | SIM card for GSM modem & Telephone line for Voice modem (If required at User) | User
23 | Network cable / Serial cable for alarms data communication Required cable to be lay from S/w or ES system. Alarms printing to be done. | User
24 | Ethernet network Infrastructure for Mailing and data communication (Between DCS Station/ AIMS System to User Intranet) (If required at User) | User
25 | Place identification for PC, Monitor - System to be place | User
26 | Priority wise tag list, Area wise file or Alarm grouping file plant wise - If any customization is required to display Alarms data in excel. Excel file to be provided by End User/User to M/s. SSM. | End User
27 | Critical tag list to be provided for AIMS system for SMS notification facility | End User
28 | Voice call- Analogue telephone line - If required on site as per specs. | End User
29 | SMS functionality- Permanent 3G GSM SIM card for GSM Modem with full signal strength - If required on site as per specs. | End User
30 | Reports customization - Predefine formats, data or identification to be provided | End User
31 | Plant wise email matrix - Auto email shall be sent via AIMS system to respective | End User
32 | Plant wise SMS Matrix - Contact number for critical tag SMS notification | End User
33 | Conditions to be provided by End User – to demonstrate functionality related to dynamic alarms, advance rule base, | End User
B | Software Requirements - Make arrangement from Store to Plant
1 | X-Force Alarm Management System - Software Media DVD | SSM
2 | MSSQL Server R2 - 2012 | SSM
3 | Operating System- Win 8.1 Pro or Higher / Win SRV 2008 or Higher | User
4 | IIS For X-Force AIMS Web Reporting | User
5 | Antivirus for AIMS | User
6 | Microsoft office- Latest | User
C | If communication over Serial/Ethernet Protocol, Alarm line/live print must be enable in DCS/ SOE to get Alarms in to AIMS system | User
| If communication over OPC protocol, OPC AE must be available at DCS side and it should be readable form/ printable form. | User
D | Other Requirements (If required Email facility)
| For Mailing of Reports | User |  | If it is required on site to initiate auto email for reports from AIMS system, required Email functionality from User end.
A. Intranet IP Address for X-Force AIMS System with authentication for sending mail.
B. List of persons for sending report through mail.
| For Sending of Reports through SMTP | User
A. E-mail address or SMTP Address for X-force AIMS System.
B. If using SMTP Authentication for X-Force AIMS IP address on Exchange Server.
E | IP Address for AIMS SYSTEM - ( DCS network ) | User
F | Required Power Supply Arrangements for all Hardware | User
Note on B24: DCS station to AIMS system communication cable for alarms printing. (Ethernet or Serial)