## Slide 1
Project Management

## Slide 2: What is Project Management?
  A Project is a temporary endeavor undertaken to create a unique product or services.
    It is,
    Performed by people
    Constrained by limited resources
    Planned, executed and controlled.

## Slide 3: Project Management - Phases
Initiate
Plan
Monitor & Control
Close
Execute
Project Management: A dynamic process that utilizes the appropriate resources of the organization in a controlled and structured manner, to achieve some clearly defined objectives identified as needs.

## Slide 4: Examples of Projects
Developing a new Product or service
Customize the existing one
Developing or modifying a new or modified information system
Installation of ready software with Commissioning
Supply of Resale products
Supply and service of Resale products
Services for resale, customized, own products.

## Slide 5: Types of Projects
  Engineering Projects
  Runrate Projects
  Trading.
  Trading Projects.
  Annual Maintenance Contract.
  Services & Spares

## Slide 6: Project Lifecycle

## Slide 7: Project Triangle
Scope
Time
Cost
Quality
Project Scope: The work that must be done to deliver a product with the specified features and functions.
Definition : Subdividing the major deliverables into smaller, more manageable components to provide better control
Planning : The Process of progressively elaborating the work of the project, which includes developing a written scope statement that includes the project justification, the major deliverables, and the project objectives.
Statement: The scope statement provides a documented basis for making future project decisions and for confirming or developing common understanding of project scope among the stakeholders. As the project progresses, the scope statement may need to be revised or refined to reflect approved changes to the scope of the project.
Verification: Formalizing acceptance of the project scope.

## Slide 8: Project Triangle
Scope
Time
Cost
Quality

## Slide 9: Project Triangle
Scope
Time
Cost
Quality
There are major four activities to be performed for Cost management:
Resource Planning
Cost Estimation
Cost Budgeting
Cost Control

## Slide 10: Project Quality Management
There are major three activities to be performed for Quality management:
Quality Planning
Quality Assurance
Quality Control
Simple fundamental to this is defined by Deming cycle :
PLAN: Design or révise business process components to improve results.
DO: Implement the plan and measure its performance
CHECK: Assess the measurements and report the results to decision makers
ACT: Decide on changes needed to improve the process
The Deming Cycle

## Slide 11: Project Life Cycle @ SSM
Initiate
Understand
Plan
Design and Procure
Test
Execute
Close-Out
IKOM
Get OEF
Tech. Scope
Com. Terms
Solution Review
Resource Planning
Project Schedule
Prepare EAC
Prepare FDS
Plan CKOM
CKOM
Finalize EAC
Resource Allocation
Review Final Scope
Start Development
Proceed for Procurement
Invoicing &Dispatch
Supply Payment
Internal test
FAT Call and Conduction
Invoicing & Dispatch
Review & Get ready for execution
Send Pre-requisite
Initiate Execution
Plan and conduct SAT
Prepare Closure Docs
Submit Closure Docs
Final Handover Meet
Final Invoicing
Warranty Period
Get Completion Certificate and Payment
Feedback
Hold Execution if supply payment not received

## Slide 12: Roles & Responsibilities (RACI Matrix)

## Slide 13: Monitoring and Controlling
PMO Performs following activities for monitoring and controlling.
  PM’s Weekly Review meeting for monitoring and controlling over critical Project points.
  EAC Review to monitor Project’s P&L (Fortnightly Conducted with Each PM)
  Project Review to monitor project status and timeline (Weekly Conducted)
  Billing-Collection Review (MRM) to assess planned VS Actual billing and collection (Monthly Conducted).
SSM has a Monitoring and Controlling Department recognized as PMO

## Slide 14: Tools & Templates
Order Entry Form - OEF
Internal Kick Off Meeting - IKOM
Customer Kick Off meeting - CKOM
Material Resource Planning - MRP
Finance Statement - Cash Flow sheet
Estimated at Completion - EAC
Project Review Notes - PM’s Weekly Review RAIL
RACI Matrix - RACI

## Slide 15
Questions / Queries